## GanttChart
 | time axis 2023-08-27 to 2023-10-09
| Start Date | End Date | Duration | Adjust Days | 2023-08-27: 2023-08-27; 2023-08-29: 2023-08-29; 2023-08-31: 2023-08-31; 2023-09-02: 2023-09-02; 2023-09-04: 2023-09-04; 2023-09-06: 2023-09-06; 2023-09-08: 2023-09-08; 2023-09-10: 2023-09-10; 2023-09-12: 2023-09-12; 2023-09-14: 2023-09-14; 2023-09-16: 2023-09-16; 2023-09-18: 2023-09-18; 2023-09-20: 2023-09-20; 2023-09-22: 2023-09-22; 2023-09-24: 2023-09-24; 2023-09-26: 2023-09-26; 2023-09-28: 2023-09-28; 2023-09-30: 2023-09-30; 2023-10-02: 2023-10-02; 2023-10-04: 2023-10-04; 2023-10-06: 2023-10-06; 2023-10-08: 2023-10-08
Decide Research Questions | 2023-08-27 | 2023-09-02 | 5 | 6
Decide Roles of Members | 2023-08-27 | 2023-09-02 | 5 | 6
Modelling | 2023-09-10 | 2023-09-22 | 10 | 12
Write Report | 2023-09-16 | 2023-10-06 | 15 | 20
Write Project Plan | 2023-09-02 | 2023-09-04 | 1 | 2
Data Preparation | 2023-09-04 | 2023-09-09 | 5 | 5
Evaluation of Model | 2023-09-10 | 2023-09-22 | 10 | 12
Research Methods & Software | 2023-09-02 | 2023-09-04 | 1 | 2
Source External data | 2023-08-30 | 2023-09-06 | 6 | 7
Data Analysis | 2023-09-23 | 2023-09-29 | 5 | 6
Group Presentation | 2023-09-23 | 2023-10-09 | 11 | 16
Data Science Project Plan: Group G
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Today

## Data
Student Name | Task | Start_Date | End_Date
Kin Cheang | Decide Research Questions | 2023-08-27 | 2023-09-02
Kin Cheang | Decide Roles of Members | 2023-08-27 | 2023-09-02
Kin Cheang | Literature Review | 2023-08-27 | 2023-09-02
Kin Cheang | Source External data | 2023-08-30 | 2023-09-06
Kin Cheang | Write Project Plan | 2023-09-02 | 2023-09-04
Kin Cheang | Write Report | 2023-09-16 | 2023-10-06
Kin Cheang | Presentation Slides | 2023-09-16 | 2023-10-07
Kin Cheang | Group Presentation | 2023-09-23 | 2023-10-09
Kourosh Shaban | Decide Research Questions | 2023-08-27 | 2023-09-02
Kourosh Shaban | Decide Roles of Members | 2023-08-27 | 2023-09-02
Kourosh Shaban | Source External data | 2023-08-30 | 2023-09-06
Kourosh Shaban | Write Project Plan | 2023-09-02 | 2023-09-04
Kourosh Shaban | Data Preparation | 2023-09-04 | 2023-09-09
Kourosh Shaban | Evaluation of Model | 2023-09-10 | 2023-09-22
Kourosh Shaban | Modelling | 2023-09-10 | 2023-09-22
Kourosh Shaban | Write Report | 2023-09-16 | 2023-10-06
Kourosh Shaban | Data Analysis | 2023-09-23 | 2023-09-29
Kourosh Shaban | Group Presentation | 2023-09-23 | 2023-10-09
Alexander Hodges | Decide Research Questions | 2023-08-27 | 2023-09-02
Alexander Hodges | Decide Roles of Members | 2023-08-27 | 2023-09-02
Alexander Hodges | Source External data | 2023-08-30 | 2023-09-06
Alexander Hodges | Write Project Plan | 2023-09-02 | 2023-09-04
Alexander Hodges | Research Methods & Software | 2023-09-02 | 2023-09-04
Alexander Hodges | Data Preparation | 2023-09-04 | 2023-09-09
Alexander Hodges | Evaluation of Model | 2023-09-10 | 2023-09-22
Alexander Hodges | Modelling | 2023-09-10 | 2023-09-22
Alexander Hodges | Write Report | 2023-09-16 | 2023-10-06
Alexander Hodges | Data Analysis | 2023-09-23 | 2023-09-29
Alexander Hodges | Group Presentation | 2023-09-23 | 2023-10-09
Zining Wang | Decide Research Questions | 2023-08-27 | 2023-09-02
Zining Wang | Decide Roles of Members | 2023-08-27 | 2023-09-02
Zining Wang | Literature Review | 2023-08-27 | 2023-09-02
Zining Wang | Source External data | 2023-08-30 | 2023-09-06
Zining Wang | Write Project Plan | 2023-09-02 | 2023-09-04
Zining Wang | Research Methods & Software | 2023-09-02 | 2023-09-04
Zining Wang | Data Preparation | 2023-09-04 | 2023-09-09
Zining Wang | Evaluation of Model | 2023-09-10 | 2023-09-22
Zining Wang | Modelling | 2023-09-10 | 2023-09-22
Zining Wang | Write Report | 2023-09-16 | 2023-10-06
Zining Wang | Data Analysis | 2023-09-23 | 2023-09-29
Zining Wang | Group Presentation | 2023-09-23 | 2023-10-09

## PivotTable
Row Labels | Min of Start_Date | Max of End_Date
Data Analysis | 45192 | 45198
Data Preparation | 45173 | 45178
Decide Research Questions | 45165 | 45171
Decide Roles of Members | 45165 | 45171
Evaluation of Model | 45179 | 45191
Group Presentation | 45192 | 45208
Modelling | 45179 | 45191
Research Methods & Software | 45171 | 45173
Source External data | 45168 | 45175
Write Project Plan | 45171 | 45173
Write Report | 45185 | 45205
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.